## User Stories
Task | Estimates
Total | 47
Viewing by category | 3
Include Developer Provided Description | 2
Public Discussions | 1
Various Platforms | 1
Customized Filteration for searches | 5
User request additions + duplicate checker | 7
Simple and sleek interface
Consistent Search Bar | 5
Outstanding request | 5
Login before contributing forums | 7
Moderator - delete posts from forums | 2
Database | 0
Redirected to app download page | 2
Desktop & Mobile | 7

## Chart
Iterations | Estimates | Ideal
0 | 49 | 49
1 | 49 | 48
2 | 49 | 47
3 | 49 | 46
4 | 47 | 45
5 |  | 44
6 |  | 43
7 |  | 42
8 |  | 41
9 |  | 40
10 |  | 39
11 |  | 38
12 |  | 37
13 |  | 36
14 |  | 35
15 |  | 34
16 |  | 33
17 |  | 32
18 |  | 31
19 |  | 30
20 |  | 29
21 |  | 28
22 |  | 27
23 |  | 26
24 |  | 25
25 |  | 24
26 |  | 23
27 |  | 22
28 |  | 21
29 |  | 20
30 |  | 19
31 |  | 18
32 |  | 17
33 |  | 16
34 |  | 15
35 |  | 14
36 |  | 13
37 |  | 12
38 |  | 11
39 |  | 10
40 |  | 9
41 |  | 8
42 |  | 7
43 |  | 6
44 |  | 5
45 |  | 4
46 |  | 3
47 |  | 2
48 |  | 1
49 |  | 0