## User Stories
Task | Estimates | 13
Total | 55 | 5
Viewing by category | 3 | 3
Include Developer Provided Description | 2 | 5
Public Discussions | 7
Various Platforms | 1
Customized Filteration for searches | 5
User request additions + duplicate checker | 7
Simple and sleek interface
Consistent Search Bar | 3
Outstanding request | 5
Login before contributing forums | 6
Configure App User classes | 3
Moderator - delete posts from forums | 2
Database | 10
Redirected to app download page | 2
Desktop & Mobile | 7
HTML stuff | 5

## Chart
Days | Estimates | Ideal | Actual | Velocity
0 | 49 | 63 | 49
1 | 49 | 62 | 49 |  | 63.58
2 | 51 | 61 | 49
3 | 56 | 60 | 49
4 | 64 | 59 | 49
5 | 65 | 58 | 65
6 | 64 | 57 | 64
7 | 63 | 56 | 62
8 | 62 | 55 | 60
9 | 59 | 54 | 59
10 | 57 | 53 | 58
11 | 53 | 52 | 51
12 | 51 | 51 | 51
13 | 51 | 50
14 | 51 | 49
15 | 51 | 48
16 | 50 | 47
17 | 50 | 46
18 | 50 | 45
19 | 49 | 44
20 | 49 | 43
21 | 48 | 42
22 | 48 | 41
23 | 47 | 40
24 | 47 | 39
25 | 47 | 38
26 | 46 | 37
27 | 46 | 36
28 | 46 | 35
29 | 44 | 34
30 | 42 | 33
31 | 40 | 32
32 | 37 | 31
33 | 35 | 30
34 | 31 | 29
35 | 29 | 28
36 | 28 | 27
37 | 27 | 26
38 | 26 | 25
39 | 25 | 24
40 | 24 | 23
41 | 23 | 22
42 | 22 | 21
43 | 21 | 20
44 | 20 | 19
45 | 19 | 18
46 | 18 | 17
47 | 17 | 16
48 | 16 | 15
49 | 15 | 14
50 | 14 | 13
51 | 13 | 12
52 | 12 | 11
53 | 11 | 10
54 | 10 | 9
55 | 9 | 8
56 | 8 | 7
57 | 7 | 6
58 | 6 | 5
59 | 5 | 4
60 | 4 | 3
61 | 3 | 2
62 | 2 | 1
63 | 1 | 0