## User Stories
Task | Estimates | 13
Total | 55 | 5
Viewing by category | 3 | 3
Include Developer Provided Description | 2 | 5
Public Discussions | 7
Various Platforms | 1
Customized Filteration for searches | 5
User request additions + duplicate checker | 7
Simple and sleek interface
Consistent Search Bar | 3
Outstanding request | 5
Login before contributing forums | 6
Configure App User classes | 3
Moderator - delete posts from forums | 2
Database | 10
Redirected to app download page | 2
Desktop & Mobile | 7
HTML stuff | 5

## Tasks
Tasks | 36
Plan and Design Database | 5
Make the proper results.. | 2
Forum class | 5
Edit and config app class | 2
Search bar | 3
Servelets | 5
Get info… | 14

## Chart
Days | Estimates | Ideal | Actual | Velocity
0 | 70 | 49 | 49 | 0.7
1 | 70 | 48 | 49 | 0.7 | 63.58
2 | 70 | 47 | 49 | 0.7
3 | 70 | 46 | 49 | 0.7
4 | 70 | 45 | 49 | 0.7
5 | 59 | 44 | 65 | 1.1017
6 | 58 | 43 | 64 | 1.1034
7 | 57 | 42 | 62 | 1.0877
8 | 56 | 41 | 60 | 1.0714
9 | 55 | 40 | 59 | 1.0727
10 | 54 | 39 | 58 | 1.0741
11 | 53 | 38 | 51 | 0.96226
12 | 51 | 37 | 51 | 1
13 | 51 | 36 | 50 | 0.98039
14 | 48 | 35 | 48 | 1
15 | 47 | 34 | 47 | 1
16 | 46 | 33 | 46 | 1
17 | 45 | 32 | 45 | 1
18 | 43 | 31 | 43 | 1
19 | 42 | 30 | 42 | 1
20 | 40 | 29 | 40 | 1
21 | 38 | 28 | 38 | 1
22 | 38 | 27 | 38 | 1
23 | 38 | 26 | 38 | 1
24 | 37 | 25 | 37 | 1
25 | 36 | 24 | 37 | 1.0278
26 | 35 | 23 | 37 | 1.0571
27 | 34 | 22 | 36 | 1.0588
28 | 33 | 21 | 36 | 1.0909
29 | 32 | 20 | 34 | 1.0625
30 | 31 | 19 | 32 | 1.0323
31 | 30 | 18 | 30 | 1
32 | 29 | 17 | 28 | 0.96552
33 | 28 | 16 | 27 | 0.96429
34 | 27 | 15 | 26 | 0.96296
35 | 26 | 14 | 24 | 0.92308
36 | 25 | 13 | 22 | 0.88
37 | 24 | 12 | 20 | 0.83333
38 | 23 | 11 | 18 | 0.78261
39 | 22 | 10 | 16 | 0.72727
40 | 21 | 9 | 14 | 0.66667
41 | 20 | 8 | 12 | 0.6
42 | 19 | 7 | 10 | 0.52632
43 | 18 | 6 | 8 | 0.44444
44 | 17 | 5 | 7 | 0.41176
45 | 16 | 4 | 6 | 0.375
46 | 15 | 3 | 5 | 0.33333
47 | 14 | 2 | 4 | 0.28571
48 | 13 | 1 | 3 | 0.23077