## User Stories
Task | Estimates
Total | 47
Viewing by category | 3
Include Developer Provided Description | 2
Public Discussions | 1
Various Platforms | 1
Customized Filteration for searches | 5
User request additions + duplicate checker | 7
Simple and sleek interface
Consistent Search Bar | 5
Outstanding request | 5
Login before contributing forums | 7
Moderator - delete posts from forums | 2
Database | 0
Redirected to app download page | 2
Desktop & Mobile | 7

## Chart
Iterations | Estimates | Ideal | Velocity
0 | 49 | 49
1 | 49 | 48
2 | 49 | 47
3 | 49 | 46
4 | 47 | 45
5 | 45 | 44
6 | 43 | 43
7 | 41 | 42
8 | 39 | 41
9 | 37 | 40
10 | 35 | 39
11 | 33 | 38
12 | 31 | 37
13 | 29 | 36
14 | 27 | 35
15 | 25 | 34
16 | 23 | 33
17 | 21 | 32
18 | 19 | 31
19 | 17 | 30
20 | 15 | 29
21 | 13 | 28
22 | 11 | 27
23 | 9 | 26
24 | 7 | 25
25 | 5 | 24
26 | 3 | 23
27 | 1 | 22
28 |  | 21
29 |  | 20
30 |  | 19
31 |  | 18
32 |  | 17
33 |  | 16
34 |  | 15
35 |  | 14
36 |  | 13
37 |  | 12
38 |  | 11
39 |  | 10
40 |  | 9
41 |  | 8
42 |  | 7
43 |  | 6
44 |  | 5
45 |  | 4
46 |  | 3
47 |  | 2
48 |  | 1
49 |  | 0