## User Stories
Task | Estimates
Total | 60
Viewing by category | 3
Include Developer Provided Description | 2
Public Discussions | 7
Various Platforms | 1
Customized Filteration for searches | 5
User request additions + duplicate checker | 7
Simple and sleek interface
Consistent Search Bar | 3
Outstanding request | 5
Login before contributing forums | 6
Moderator - delete posts from forums | 2
Database | 10
Redirected to app download page | 2
Desktop & Mobile | 7

## Chart
Days | Estimates | Ideal | Actual | Velocity
0 | 49 | 49 | 49
1 | 49 | 48 | 49 |  | 63.58
2 | 51 | 47 | 49
3 | 56 | 46 | 49
4 | 64 | 45 | 49
5 | 65 | 44 | 65
6 | 64 | 43 | 64
7 | 63 | 42 | 62
8 | 62 | 41 | 60
9 | 59 | 40
10 | 57 | 39
11 | 53 | 38
12 | 51 | 37
13 | 46 | 36
14 | 45 | 35
15 | 44 | 34
16 | 42 | 33
17 | 40 | 32
18 | 37 | 31
19 | 35 | 30
20 | 31 | 29
21 | 29 | 28
22 | 28 | 27
23 | 27 | 26
24 | 26 | 25
25 | 25 | 24
26 | 24 | 23
27 | 23 | 22
28 | 22 | 21
29 | 21 | 20
30 | 20 | 19
31 | 19 | 18
32 | 18 | 17
33 | 17 | 16
34 | 16 | 15
35 | 15 | 14
36 | 14 | 13
37 | 13 | 12
38 | 12 | 11
39 | 11 | 10
40 | 10 | 9
41 | 9 | 8
42 | 8 | 7
43 | 7 | 6
44 | 6 | 5
45 | 5 | 4
46 | 4 | 3
47 | 3 | 2
48 | 2 | 1
49 | 1 | 0