## User Stories
Task | Estimates | 13
Total | 55 | 5
Viewing by category | 3 | 3
Include Developer Provided Description | 2 | 5
Public Discussions | 7
Various Platforms | 1
Customized Filteration for searches | 5
User request additions + duplicate checker | 7
Simple and sleek interface
Consistent Search Bar | 3
Outstanding request | 5
Login before contributing forums | 6
Configure App User classes | 3
Moderator - delete posts from forums | 2
Database | 10
Redirected to app download page | 2
Desktop & Mobile | 7
HTML stuff | 5

## Tasks
Tasks | 36
Plan and Design Database | 5
Make the proper results.. | 2
Forum class | 5
Edit and config app class | 2
Search bar | 3
Servelets | 5
Get info… | 14

## Chart
Days | Estimates | Ideal | Actual | Velocity
0 | 49 | 61 | 49
1 | 49 | 60 | 49 |  | 63.58
2 | 51 | 59 | 49
3 | 56 | 58 | 49
4 | 64 | 57 | 49
5 | 65 | 56 | 65
6 | 64 | 55 | 64
7 | 63 | 54 | 62
8 | 62 | 53 | 60
9 | 59 | 52 | 59
10 | 57 | 51 | 58
11 | 53 | 50 | 51
12 | 51 | 49 | 51
13 | 51 | 48 | 50
14 | 48 | 47 | 48
15 | 47 | 46 | 47
16 | 46 | 45 | 46
17 | 45 | 44 | 45
18 | 43 | 43 | 43
19 | 42 | 42 | 42
20 | 40 | 41 | 40
21 | 38 | 40 | 38
22 | 38 | 39 | 38
23 | 38 | 38 | 38
24 | 37 | 37 | 37
25 | 36 | 36 | 37
26 | 35 | 35 | 37
27 | 34 | 34 | 36
28 | 33 | 33 | 36
29 | 32 | 32
30 | 31 | 31
31 | 30 | 30
32 | 29 | 29
33 | 28 | 28
34 | 27 | 27
35 | 26 | 26
36 | 25 | 25
37 | 24 | 24
38 | 23 | 23
39 | 22 | 22
40 | 21 | 21
41 | 20 | 20
42 | 19 | 19
43 | 18 | 18
44 | 17 | 17
45 | 16 | 16
46 | 15 | 15
47 | 14 | 14
48 | 13 | 13
49 | 12 | 12
50 | 11 | 11
51 | 10 | 10
52 | 9 | 9
53 | 8 | 8
54 | 7 | 7
55 | 6 | 6
56 | 5 | 5
57 | 4 | 4
58 | 3 | 3
59 | 2 | 2
60 | 1 | 1
61 | 0 | 0
62 | 0 | 0
63 | 0 | 0